PhD Progress Report

Reporting period: 1 July 2025 to 31 December 2025    |    Report no.: 1 (first six-month report)

EXAMPLE ONLY. Every name, number, date and result in this document is invented. It shows how a first six-month report can look. Do not copy the wording: write about your own work. Your university may have its own form; use that form if it does. The blank template is at https://www.letrelay.com/blog/phd-progress-report-format-sample

# 1. Student and project details

| Name | A. Sample (fictional) |
| --- | --- |
| Registration / student number | EU-2025-0000 (fictional) |
| Department and university | Department of Environmental Science, Example University |
| Programme and start date | Full-time PhD, started 1 July 2025 |
| Supervisor(s) | Dr B. Example |
| Committee members (research advisory, doctoral or thesis committee) | Dr C. Example; Prof D. Example |
| Date submitted | 10 January 2026 |

# 2. Working title of the thesis

Effects of crop-residue mulching on soil moisture and wheat yield in semi-arid fields. (Unchanged since registration.)

# 3. Summary

In this period I finished the literature review, designed and set up the field experiment (three mulched and three unmulched plots at the university farm) and collected the first soil moisture data. Early readings show higher soil moisture in the mulched plots at 10 cm depth, by about 3 percentage points on average; this is one season and not yet tested statistically. The main problem was a five-week delay in getting the moisture sensors, which I covered with hand sampling. Next period I will complete the winter wheat season, analyse the data and draft the methods chapter.

# 4. Objectives and progress

| # | Objective (from your approved plan) | Planned for this period | Status | Comment |
| --- | --- | --- | --- | --- |
| 1 | Review the literature on mulching and soil moisture in semi-arid wheat | Review of about 40 papers | Done | Draft review (6,200 words) sent to my supervisor on 12 November. |
| 2 | Design and set up the field experiment | Plots ready by 1 October | Done, 2 weeks late | Six plots: two treatments, three replicates each. |
| 3 | Collect soil moisture data through the season | Weekly readings from October | Done, method changed | 11 weekly readings: 5 by hand sampling before the sensors arrived, 6 with sensors (see section 6). |
| 4 | Complete the required research methods course | Pass the course | Done | Passed in October. |

# 5. Work done and results

## 5.1 Work completed

Read and summarised 41 papers and wrote a 6,200-word review of mulching effects on soil moisture. Chose a randomised block design after a meeting with Dr C. Example. Prepared six 5 m x 5 m plots on 29 September and sowed winter wheat on 14 October. From 21 October I recorded soil moisture weekly at 10 cm and 30 cm depth.

## 5.2 Results so far

At 10 cm depth the mulched plots held about 3 percentage points more moisture than the unmulched plots (average of 11 weekly readings per plot). At 30 cm the difference was smaller and varied between weeks. These are first-season observations: I have not yet run any statistical test, and rainfall in November may explain part of the difference. Figure 1 (attached) shows the weekly averages.

## 5.3 What this means for the thesis

If the pattern holds through spring, results chapter 1 will report the moisture effect and chapter 2 the yield effect. I will need a second season of data for the yield chapter.

# 6. Problems and changes to the plan

| Problem | Effect on the work | What you are doing about it | Help you need (from whom) |
| --- | --- | --- | --- |
| Moisture sensors arrived five weeks late | Five weekly readings had to be taken by hand (less precise) | Used weekly hand sampling (oven-dry method) until the sensors were installed on 25 November | Friday lab oven access: Dr B. Example to confirm with the lab manager |

# 7. Courses, training and teaching

| Item | Dates | Status or grade |
| --- | --- | --- |
| Research methods and ethics (required) | July to October 2025 | Passed |
| Statistics for field experiments | November 2025 to February 2026 | In progress |

# 8. Publications and presentations

| Type (paper, talk, poster) | Title and venue | Status (planned, submitted, accepted, published) | Date |
| --- | --- | --- | --- |
| Poster | Mulching and soil moisture: first results. Departmental research day | Presented | Dec 2025 |
| Paper 1 | Review of mulching effects in semi-arid wheat systems | Planned: submit by May 2026 | May 2026 |

# 9. Thesis chapter status

| Chapter | Status (not started, outline, draft, revised) | Target date for next draft |
| --- | --- | --- |
| 1. Introduction | Outline | June 2026 |
| 2. Literature review | First draft (from the review) | March 2026 (revise) |
| 3. Methods | Not started | March 2026 |
| 4. Results: soil moisture | Not started | September 2026 |

# 10. Plan for the next period

| Task | Start | End | What you will have to show |
| --- | --- | --- | --- |
| Finish the winter wheat season: weekly moisture readings | Jan 2026 | Apr 2026 | Complete 24-week data set |
| Draft the methods chapter | Feb 2026 | Mar 2026 | 10-page draft to supervisor |
| Analyse moisture data (mixed model in R) | Apr 2026 | May 2026 | Tables and figures for chapter 4 |
| Outline and write paper 1 (review) | Apr 2026 | May 2026 | Submitted manuscript |

# 11. Support or resources needed

Friday access to the drying oven. A meeting with Dr C. Example in February to check the statistical approach before I analyse the data.

# 12. Student declaration

I confirm that this report is accurate and that I have discussed it with my supervisor.

Signed: A. Sample (fictional)          Date: 10 January 2026

# 13. Supervisor's assessment (completed by the supervisor)

Progress in this period:

☐ Satisfactory, on schedule        ☒ Satisfactory, with suggestions        ☐ Unsatisfactory

Comments: Good start. The five-week sensor delay was handled sensibly. Compare the hand-sampled weeks with the sensor weeks so the two methods can be checked against each other, and start the methods chapter now while the details are fresh.

Supervisor: Dr B. Example (fictional)          Date: 14 January 2026

# 14. Committee recommendation (if your university requires it)

Not required for the first six-month report at Example University (fictional).